## Test Report
Test Summary Report
Project Name | Amazon |  | Bug Summary | Test Execution Summary |  |  |  | Test Environment
Module Name | Home Page
Test Cycle | Regression Testing- Cycle 1 |  | Total Test Cases | Total Test Cases | 25 |  |  | Browser | Chrome
Test Date | 2026-04-24 |  |  | Test Executed | 25 |  |  | Device | Laptop/Desktop
Reported Date | 2026-04-25 |  | Test Executed | Passed Tests | 21 |  |  | OS | Windows 10
QA Manager | XXXX |  |  | Failed Tests | 4 |  |  | Version
QA Lead |  |  |  | Tests Pending | 0 |  |  | Build | #2
Test Type | Functional Testing |  |  | Tests Blocked | 0 |  |  | Network | Wi-fi/Broadband
Scope Of Testing |  |  |  |  | Test Case Results(Sample)
In Scope | 1.Navigation of First Header (Search bar,Cart,Menu) 2.Navigation of Second Header(Rufus AI,Prime Video and others) 3.Smooth Scrolling behaviour 4.Page Refresh Functionality |  |  |  | TC_ID | Test Scenario | Expected Result |  | Actual Result | Status
[5 empty] | TC_001 | Logo Click Navigation | User should be redirected to homepage from any page |  | As expected | Pass
[5 empty] | TC_002 | Search Bar Navigation | User should be shown relevant search product |  | As expected | Pass
[5 empty] | TC_003 | Verify Refresh Functionality | User should be taken back to the top of the page |  | Not Working | Fail
Out of Scope | 1.Payment Method Functionality 2.Order Tracking
[5 empty] | TC_004 | Click on "ALL" menu | Category panel opens |  | As expected | Pass
Defect Summary |  |  |  |  | Defect Details(Open)
Severity | Count | Percentage |  |  | Bug_ID | Description |  |  | Severity | Status
Critical | 0 | 0% |  |  | BUG_001 | For invalid search (special characters) error toast message is not shown |  |  | High | Open
High | 1 | 25% |  |  | BUG_002 | After clearing browser history, item stays until page refresh |  |  | Medium | Open
Medium | 2 | 50% |  |  | BUG_003 | After page refresh,user is not taken back to the top of homepage |  |  | Low | Open
Low | 1 | 25% |  |  | BUG_004 | No products displayed when searching with empty keyword after selecting category |  |  | Medium | Open
Total | 4 | 100%